## Migration Checklist
Oracle EBS to Fusion Cloud Migration Governance Checklist
IZU Solutions LLC ¦ Oracle ERP Migration Advisory
Item # | Section | Checklist Item | Owner | Status | Priority | Notes
Governance Structure Setup
1 | Governance Structure Setup | Steering committee chartered with defined membership and authority |  |  | High
2 | Governance Structure Setup | RACI matrix documented and distributed to all workstream leads |  |  | High
3 | Governance Structure Setup | Decision rights defined — approval thresholds and escalation levels |  |  | High
4 | Governance Structure Setup | Escalation path confirmed and tested with Steering Committee |  |  | High
5 | Governance Structure Setup | Governance meeting cadence set — weekly status, bi-weekly steering |  |  | Medium
6 | Governance Structure Setup | Program charter signed off by executive sponsor |  |  | High
7 | Governance Structure Setup | Budget baseline established and approved |  |  | High
8 | Governance Structure Setup | Program communications plan published |  |  | Medium
9 | Governance Structure Setup | Risk and issue management process activated |  |  | High
Scope & Change Management
10 | Scope & Change Management | Scope baseline documented and signed off by all stakeholders |  |  | High
11 | Scope & Change Management | Change control process active — change request template in use |  |  | High
12 | Scope & Change Management | Impact assessment template in use for all scope changes |  |  | High
13 | Scope & Change Management | Scope change log maintained and reviewed weekly |  |  | Medium
14 | Scope & Change Management | Out-of-scope items documented and agreed with SI partner |  |  | Medium
15 | Scope & Change Management | Phased deployment plan confirmed (if applicable) |  |  | High
16 | Scope & Change Management | Configuration workbook baseline signed off |  |  | High
17 | Scope & Change Management | Gap analysis complete and remediation plan active |  |  | High
18 | Scope & Change Management | Business process re-engineering decisions documented |  |  | Medium
Data Migration Governance
19 | Data Migration Governance | Data owners assigned per domain (GL, AP, AR, FA, HCM, etc.) |  |  | High
20 | Data Migration Governance | Data quality baseline established — current-state issues logged |  |  | High
21 | Data Migration Governance | Data remediation tasks tracked with owners and target dates |  |  | High
22 | Data Migration Governance | Data extraction scripts validated against source system |  |  | High
23 | Data Migration Governance | Data transformation rules documented and approved |  |  | High
24 | Data Migration Governance | Mock migration #1 complete — results reviewed and gaps logged |  |  | High
25 | Data Migration Governance | Mock migration #2 complete — reconciliation counts match |  |  | High
26 | Data Migration Governance | Data migration cutover plan approved |  |  | High
27 | Data Migration Governance | Legacy data archival plan confirmed and approved |  |  | Medium
Implementation Partner Management
28 | Implementation Partner Management | SI partner RACI confirmed and aligned with internal RACI |  |  | High
29 | Implementation Partner Management | Deliverable acceptance criteria defined for all major deliverables |  |  | High
30 | Implementation Partner Management | Hypercare SLA agreed — response times and escalation defined |  |  | High
31 | Implementation Partner Management | Invoice milestone plan confirmed and aligned to deliverables |  |  | Medium
32 | Implementation Partner Management | Change order process active — approval thresholds defined |  |  | High
33 | Implementation Partner Management | SI performance scorecard in use — reviewed monthly |  |  | Medium
34 | Implementation Partner Management | Key SI personnel changes require program manager approval |  |  | High
35 | Implementation Partner Management | Knowledge transfer plan agreed — documentation standards defined |  |  | Medium
36 | Implementation Partner Management | SI partner security and access provisioning confirmed |  |  | Medium
Cutover & Go-Live Readiness
37 | Cutover & Go-Live Readiness | Go/No-Go criteria defined and approved by Steering Committee |  |  | High
38 | Cutover & Go-Live Readiness | Rollback plan documented and approved — decision authority defined |  |  | High
39 | Cutover & Go-Live Readiness | Business readiness sign-off obtained from all business units |  |  | High
40 | Cutover & Go-Live Readiness | Post go-live support model confirmed — hypercare team identified |  |  | High
41 | Cutover & Go-Live Readiness | Cutover schedule tested in dry run and approved |  |  | High
42 | Cutover & Go-Live Readiness | Legacy system decommission plan confirmed |  |  | Medium
43 | Cutover & Go-Live Readiness | Training completion tracked — minimum 90% completion required |  |  | High
44 | Cutover & Go-Live Readiness | Executive go-live communication approved and scheduled |  |  | Medium
45 | Cutover & Go-Live Readiness | Day 1 support command center roster and schedule confirmed |  |  | High