## ERP Governance Checklist
ERP Program Governance Checklist
IZU Solutions LLC ¦ Applicable to Oracle Fusion Cloud & SAP S/4HANA Programs
Item # | Section | Checklist Item | Responsible Party | Status | Priority | Notes
Governance Structure Setup
1 | Governance Structure Setup | Steering committee chartered with membership, authority, and decision thresholds |  |  | High
2 | Governance Structure Setup | RACI matrix documented — all workstreams covered with clear ownership |  |  | High
3 | Governance Structure Setup | Decision rights defined — approval thresholds for budget, scope, and resources |  |  | High
4 | Governance Structure Setup | Escalation path confirmed and communicated to all stakeholders |  |  | High
5 | Governance Structure Setup | Governance calendar published — steering, status, and workstream cadence |  |  | Medium
6 | Governance Structure Setup | Program charter signed off by executive sponsor and PMO Director |  |  | High
7 | Governance Structure Setup | Program communications plan approved and activated |  |  | Medium
8 | Governance Structure Setup | Stakeholder register complete and engagement plan active |  |  | Medium
9 | Governance Structure Setup | Program management tool (Smartsheet, MS Project, etc.) configured |  |  | Low
Scope & Schedule Baseline
10 | Scope & Schedule Baseline | Scope baseline documented and signed off by all impacted business units |  |  | High
11 | Scope & Schedule Baseline | Schedule baselined in project management tool with resource assignments |  |  | High
12 | Scope & Schedule Baseline | Critical path identified and monitored weekly |  |  | High
13 | Scope & Schedule Baseline | Dependencies mapped — internal and external (vendor, regulatory, data) |  |  | High
14 | Scope & Schedule Baseline | Milestone plan published and agreed with SI partner |  |  | High
15 | Scope & Schedule Baseline | Change control process active — change request form in use |  |  | High
16 | Scope & Schedule Baseline | Scope change log maintained and reviewed at each steering meeting |  |  | Medium
17 | Scope & Schedule Baseline | Phase gate criteria defined for each program phase |  |  | High
18 | Scope & Schedule Baseline | Resource plan baselined — FTE and contractor allocations confirmed |  |  | Medium
19 | Scope & Schedule Baseline | Project budget baseline established and approved by Finance |  |  | High
Risk & Issue Management
20 | Risk & Issue Management | Risk register active and reviewed weekly by program team |  |  | High
21 | Risk & Issue Management | Risk owners assigned — each risk has a named accountable owner |  |  | High
22 | Risk & Issue Management | Issue log maintained — all issues tracked with owners and target dates |  |  | High
23 | Risk & Issue Management | Escalation SLAs defined — critical issues escalated within 24 hours |  |  | High
24 | Risk & Issue Management | Weekly risk review scheduled in program cadence |  |  | Medium
25 | Risk & Issue Management | Top 10 risks reported to Steering Committee monthly |  |  | High
26 | Risk & Issue Management | Contingency budget reserved for high-probability risks |  |  | Medium
27 | Risk & Issue Management | Risk appetite defined and approved by executive sponsor |  |  | Medium
28 | Risk & Issue Management | Third-party risk (SI partner performance) monitored and tracked |  |  | Medium
29 | Risk & Issue Management | Regulatory and compliance risks identified and mapped to controls |  |  | High
Vendor & SI Management
30 | Vendor & SI Management | Contract milestones defined and linked to payment schedule |  |  | High
31 | Vendor & SI Management | Deliverable acceptance criteria agreed for all major deliverables |  |  | High
32 | Vendor & SI Management | Change order process active — scope changes require written approval |  |  | High
33 | Vendor & SI Management | SI partner performance scorecard in use — reviewed monthly |  |  | Medium
34 | Vendor & SI Management | SI resourcing plan confirmed — key personnel locked for program duration |  |  | High
35 | Vendor & SI Management | Knowledge transfer obligations defined in contract |  |  | High
36 | Vendor & SI Management | SI partner security provisioning and access governance confirmed |  |  | High
37 | Vendor & SI Management | Invoice review process established — Finance reviews against milestones |  |  | Medium
Quality & Controls
38 | Quality & Controls | QA checkpoints scheduled at each phase gate |  |  | High
39 | Quality & Controls | Controls design reviewed by Internal Audit or external GRC advisor |  |  | High
40 | Quality & Controls | SoD analysis complete for all in-scope Oracle or SAP roles |  |  | High
41 | Quality & Controls | Audit readiness plan active — documentation standards enforced |  |  | High
42 | Quality & Controls | Testing sign-off process defined — business owner sign-off required |  |  | High
43 | Quality & Controls | Defect management process active — severity definitions documented |  |  | High
44 | Quality & Controls | Performance testing plan approved and scheduled |  |  | Medium
45 | Quality & Controls | Security testing (penetration, access) plan approved |  |  | High
46 | Quality & Controls | Data quality gates defined — minimum quality thresholds for go-live |  |  | High
Go/No-Go Criteria
47 | Go/No-Go Criteria | Business readiness confirmed — training completion ≥90%, super users ready |  |  | High
48 | Go/No-Go Criteria | Technical readiness confirmed — no open Critical/High defects |  |  | High
49 | Go/No-Go Criteria | Post go-live support model defined — hypercare team identified |  |  | High
50 | Go/No-Go Criteria | Rollback plan approved — decision authority and triggers defined |  |  | High
51 | Go/No-Go Criteria | Go-live communications sent to all end users |  |  | Medium
52 | Go/No-Go Criteria | Executive sponsor final go/no-go sign-off obtained |  |  | High
53 | Go/No-Go Criteria | Legacy system decommission or read-only plan confirmed |  |  | Medium
54 | Go/No-Go Criteria | Day 1 command center roster, schedule, and escalation list published |  |  | High
55 | Go/No-Go Criteria | Post go-live success metrics defined and baseline established |  |  | Medium