## Go-Live Checklist
Oracle Fusion Cloud Go-Live Readiness Checklist
IZU Solutions LLC ¦ Enterprise Technology Advisory
Item # | Section | Checklist Item | Owner | Status | Due Date | Notes
Financial Controls Validation
1 | Financial Controls Validation | SoD configuration reviewed and approved by Internal Audit
2 | Financial Controls Validation | Role assignments validated against approved access matrix
3 | Financial Controls Validation | Access control sign-off obtained from IT Security
4 | Financial Controls Validation | Chart of Accounts validated and reconciled to legacy
5 | Financial Controls Validation | Period close process tested end-to-end in UAT environment
6 | Financial Controls Validation | Financial controls design documented and signed off
7 | Financial Controls Validation | GL posting rules validated against business requirements
8 | Financial Controls Validation | Approval workflow for journal entries tested and confirmed
Data Migration Sign-Off
9 | Data Migration Sign-Off | Data quality validation complete — all critical fields verified
10 | Data Migration Sign-Off | Reconciliation record counts match source system extracts
11 | Data Migration Sign-Off | Open items (open POs, invoices, AR aging) cleared or carried forward
12 | Data Migration Sign-Off | Business sign-off obtained for all migrated data domains
13 | Data Migration Sign-Off | Data migration cutover scripts tested and timed
14 | Data Migration Sign-Off | Legacy system data archived per retention policy
15 | Data Migration Sign-Off | Data migration reconciliation report approved by Finance
16 | Data Migration Sign-Off | Master data governance model confirmed post go-live
Integration Testing
17 | Integration Testing | All inbound interfaces tested with full production-volume data
18 | Integration Testing | All outbound interfaces tested and confirmed by receiving systems
19 | Integration Testing | Error handling and reprocessing procedures confirmed
20 | Integration Testing | Cutover sequence for integrations tested in dry run
21 | Integration Testing | Interface monitoring and alerting configured
22 | Integration Testing | Third-party system owners have confirmed readiness
23 | Integration Testing | API connections validated with security credentials
24 | Integration Testing | EDI/batch schedules confirmed for go-live timing
UAT Completion
25 | UAT Completion | General Ledger (GL) — UAT sign-off obtained from Finance
26 | UAT Completion | Accounts Payable (AP) — UAT sign-off obtained from AP Team
27 | UAT Completion | Accounts Receivable (AR) — UAT sign-off obtained from AR Team
28 | UAT Completion | Fixed Assets (FA) — UAT sign-off obtained from Accounting
29 | UAT Completion | HCM Payroll — UAT sign-off obtained from HR
30 | UAT Completion | Defect log reviewed — all Critical/High defects closed
31 | UAT Completion | Regression testing complete after defect resolution
32 | UAT Completion | Performance testing results reviewed and approved
Hypercare Readiness
33 | Hypercare Readiness | Hypercare support model defined and communicated to business
34 | Hypercare Readiness | Escalation path documented — Tier 1/2/3 contacts confirmed
35 | Hypercare Readiness | War room schedule confirmed for first 2 weeks post go-live
36 | Hypercare Readiness | Key contacts list (IT, Finance, SI Partner) finalized and distributed
37 | Hypercare Readiness | Oracle Support SRs pre-registered for critical modules
38 | Hypercare Readiness | Hypercare SLA agreed with SI partner (response times)
39 | Hypercare Readiness | Business super users trained and available for go-live week
40 | Hypercare Readiness | Hypercare issue log template distributed to all teams
Cutover Checklist
41 | Cutover Checklist | Go/No-Go criteria documented and reviewed by Steering Committee
42 | Cutover Checklist | Rollback plan reviewed and approved — decision authority confirmed
43 | Cutover Checklist | Cutover timeline confirmed with all workstream leads
44 | Cutover Checklist | Go-live communications sent to all end users
45 | Cutover Checklist | Legacy system read-only cutover date confirmed
46 | Cutover Checklist | Cutover command center roster and schedule published
47 | Cutover Checklist | Executive go-live announcement prepared
48 | Cutover Checklist | Post go-live Day 1 support schedule distributed