## Decision Rights Matrix
Portfolio Governance Decision Rights Framework
IZU Solutions LLC ¦ R=Responsible A=Accountable C=Consulted I=Informed -=Not Involved
# | Category | Decision Description | CEO/Exec Sponsor | Portfolio Gov Board | Program Steering | PMO Director | Program Manager
1 | Initiative Approval | Approve new program/project (>$500K) | A | R | C | C | I
2 | Initiative Approval | Approve new project (<$500K) | I | A | R | C | I
3 | Initiative Approval | Reject or defer proposed initiative | A | R | C | C | I
4 | Scope Management | Approve scope change >$100K impact | A | R | C | C | I
5 | Scope Management | Approve scope change $50K-$100K impact | C | A | R | C | I
6 | Scope Management | Approve scope change <$50K impact | I | C | A | R | C
7 | Scope Management | Cancel in-flight program | A | R | C | C | I
8 | Resource Management | Approve resource reallocation (>20% change) | C | A | R | C | I
9 | Resource Management | Approve resource reallocation (<20% change) | I | C | A | R | C
10 | Budget Management | Approve budget variance >10% | A | R | C | C | I
11 | Budget Management | Approve budget variance 5-10% | C | A | R | C | I
12 | Budget Management | Approve budget variance <5% | I | C | A | R | C
13 | Budget Management | Approve unplanned budget request >$250K | A | R | C | C | I
14 | Vendor Management | Approve new vendor engagement >$500K | A | R | C | C | I
15 | Vendor Management | Approve change order >$100K | C | A | R | C | I
16 | Vendor Management | Approve change order <$100K | I | C | A | R | C
17 | Risk Management | Escalate Critical risk to Executive level | A | R | C | C | I
18 | Risk Management | Accept High-level residual risk | C | A | R | C | I
19 | Risk Management | Accept Medium-level residual risk | I | C | A | R | C
20 | Technology | Approve technology architecture change | C | A | R | C | I
21 | Technology | Approve new technology platform adoption | A | R | C | C | I
22 | Technology | Approve go-live decision | A | R | C | C | I
23 | Technology | Approve rollback decision post go-live | A | R | C | C | I
24 | Program Execution | Approve program recovery plan | A | R | C | C | I
25 | Program Execution | Pause or suspend active program phase | A | R | C | C | I
26 | Program Execution | Approve schedule variance >30 days | C | A | R | C | I
27 | Program Execution | Approve schedule variance <30 days | I | C | A | R | C
28 | Governance | Establish new governance body | A | R | C | C | I
29 | Governance | Modify governance framework | C | A | R | C | I
30 | Governance | Approve PMO standards and templates | I | C | A | R | C

## Governance Body Charters
Governance Body Charters
IZU Solutions LLC ¦ Portfolio Governance Framework
Governance Body | Purpose | Chair | Members | Meeting Cadence | Quorum Requirements | Decision Authority Limit | Escalation Path | Minutes Owner | Distribution List
Executive Steering Committee | Final decision authority for program investments, scope, and strategic direction | CEO / Executive Sponsor | CFO, CIO, CTO, Business Unit Presidents, PMO Director | Monthly (or as needed) | 3 of 5 voting members | Unlimited — final authority | Board of Directors | Executive Assistant | Steering Committee members + PMO
Portfolio Governance Board | Portfolio prioritization, resource allocation, and cross-program coordination | PMO Director / COO | Program Sponsors, IT Directors, Finance VP, Strategy Lead | Bi-weekly | 4 of 7 members | Up to $500K — escalate above | Executive Steering Committee | PMO Analyst | Portfolio stakeholders + Exec Sponsor
Program Steering Committee | Program-level oversight, issue resolution, and go/no-go decisions | Program Sponsor | Business Unit Lead, IT Director, PMO Lead, SI Partner Lead | Weekly | 3 of 5 members | Up to $100K scope change | Portfolio Governance Board | PMO Coordinator | Project team leads + Program Sponsor
Change Control Board | Evaluate and approve/reject change requests affecting scope, schedule, or budget | PMO Director | Program Manager, Business Analyst Lead, IT Architect, Finance | Weekly or as needed | Majority of members | Up to $50K — escalate above | Program Steering Committee | Change Manager | Change requestors + Program team
PMO | Standards, reporting, tooling, and governance support across all programs | PMO Director | Program Managers, Project Managers, Business Analysts, Change Managers | Weekly standup, Monthly review | Quorum not required | Standards and templates only | Portfolio Governance Board | PMO Lead | All program participants

## Escalation Thresholds
Escalation Thresholds Reference
IZU Solutions LLC ¦ Portfolio Governance Framework
# | Threshold Type | Trigger Condition | Escalate From | Escalate To | Required Timeframe | Required Documentation | Notes
1 | Budget Variance | Budget overrun >10% of approved baseline | Program Manager | Program Steering Committee | 48 hours | Variance analysis + recovery plan
2 | Budget Variance | Budget overrun >20% of approved baseline | Program Steering Committee | Portfolio Governance Board | 24 hours | Full impact assessment + options
3 | Budget Variance | Budget overrun >30% of approved baseline | Portfolio Governance Board | Executive Steering Committee | Same day | Executive briefing + decision memo
4 | Schedule Variance | Schedule slip >30 days on critical path | Program Manager | Program Steering Committee | 48 hours | Schedule recovery plan
5 | Schedule Variance | Schedule slip >60 days on critical path | Program Steering Committee | Portfolio Governance Board | 24 hours | Revised baseline + options analysis
6 | Schedule Variance | Schedule slip >90 days on critical path | Portfolio Governance Board | Executive Steering Committee | Same day | Full program review
7 | Risk Level | New Critical risk identified | Program Manager | Program Steering Committee | 24 hours | Risk description + mitigation options
8 | Risk Level | Critical risk becomes active issue | Program Steering Committee | Portfolio Governance Board | Same day | Issue brief + immediate actions
9 | Issue Severity | P1 production issue post go-live | IT Operations | CIO + Program Sponsor | Immediate | Incident brief + ETA to resolve
10 | Issue Severity | P2 business-blocking issue | Program Manager | Program Steering Committee | 4 hours | Issue description + workaround
11 | Scope Change | Scope change >$100K financial impact | Program Manager | Program Steering Committee | 48 hours | Change request + impact analysis
12 | Scope Change | Scope change >$500K financial impact | Program Steering Committee | Portfolio Governance Board | 24 hours | Full business case
13 | Vendor Performance | SI partner SLA breach | Program Manager | Program Steering Committee | 48 hours | SLA breach documentation
14 | Vendor Performance | SI partner critical resource change | Program Manager | Program Steering Committee | 24 hours | Transition plan from SI partner
15 | Vendor Performance | Vendor delivery failure — missed milestone | Program Steering Committee | Portfolio Governance Board | 24 hours | Formal notice + recovery plan
16 | Go-Live Risk | Critical go/no-go criteria not met | Program Manager | Program Steering Committee | 48 hours before go-live | Go/no-go assessment report
17 | Go-Live Risk | Rollback triggered post go-live | IT Operations | Executive Steering Committee | Immediate | Rollback decision brief
18 | Compliance | Regulatory compliance risk identified | PMO / GRC Team | Program Steering Committee | 24 hours | Compliance risk assessment
19 | Compliance | Audit finding on program controls | Internal Audit | Portfolio Governance Board | 48 hours | Audit finding + remediation plan
20 | Compliance | Data breach or security incident | IT Security | CIO + Executive Sponsor | Immediate | Incident report + containment status