## SAP GRC Checklist
SAP GRC Access Control Implementation Checklist
IZU Solutions LLC ¦ SAP GRC Advisory ¦ izusolutions.com
Item # | Section | Checklist Item | SAP Module | Owner | Status | Priority | Notes
Pre-Implementation Prerequisites
1 | Pre-Implementation Prerequisites | SAP GRC license confirmed and activated — AC, PC, RM, and EAM modules in scope confirmed | AC | GRC Team | Not Started | High
2 | Pre-Implementation Prerequisites | System landscape fully documented — DEV, QAS, and PRD systems identified with RFC connections | AC | Basis | Not Started | High
3 | Pre-Implementation Prerequisites | Basis team engaged and RFC connections (SM59) configured and tested across all systems | AC | Basis | Not Started | High
4 | Pre-Implementation Prerequisites | Current SAP authorization framework reviewed — existing roles catalogued and risk-assessed | AC | Security | Not Started | High
5 | Pre-Implementation Prerequisites | Existing SOD conflicts documented using legacy tools or manual analysis as pre-GRC baseline | AC | Security | Not Started | High
6 | Pre-Implementation Prerequisites | Business process owners identified for all key processes (FI, MM, SD, HR, BASIS) | AC | Business | Not Started | High
7 | Pre-Implementation Prerequisites | SAP GRC project team assembled — Basis, Security, GRC Functional, and Business SMEs confirmed | AC | GRC Team | Not Started | High
8 | Pre-Implementation Prerequisites | Technical design document completed and approved by architecture team | AC | IT | Not Started | Medium
9 | Pre-Implementation Prerequisites | GRC system sizing reviewed and SAP Note requirements confirmed with BASIS | AC | Basis | Not Started | Medium
10 | Pre-Implementation Prerequisites | Change management and training plan activated | AC | GRC Team | Not Started | Medium
Ruleset Configuration
11 | Ruleset Configuration | Business process ruleset validated against actual business risk — not default SAP ruleset | AC | GRC Team | Not Started | High
12 | Ruleset Configuration | Custom rules documented with business justification and approved by process owners | AC | Business | Not Started | High
13 | Ruleset Configuration | Function definitions reviewed and confirmed with business process owners | AC | GRC Team | Not Started | High
14 | Ruleset Configuration | Risk definitions (Critical/High/Medium/Low) aligned to organizational risk appetite | AC | GRC Team | Not Started | High
15 | Ruleset Configuration | Ruleset tested in DEV system — false positives reviewed and ruleset tuned | AC | GRC Team | Not Started | High
16 | Ruleset Configuration | Critical transactions (SU01, SE38, SM59, FB60, etc.) identified and protected | AC | Security | Not Started | High
17 | Ruleset Configuration | Organization-level rules configured for business units requiring granular SoD control | AC | GRC Team | Not Started | Medium
18 | Ruleset Configuration | Ruleset baseline established and documented for audit reference | AC | GRC Team | Not Started | Medium
19 | Ruleset Configuration | Ruleset sign-off obtained from Internal Audit and process owners | AC | Business | Not Started | High
20 | Ruleset Configuration | Ruleset transport from DEV to QAS validated — no regression in rule logic | AC | Basis | Not Started | High
Access Request Workflow
21 | Access Request Workflow | Access request workflow design completed — routes mapped to business approvers | AC | GRC Team | Not Started | High
22 | Access Request Workflow | MSMP (Multi-Stage Multi-Path) workflow configured and stage definitions approved | AC | GRC Team | Not Started | High
23 | Access Request Workflow | BRF+ rules configured for dynamic routing based on role risk level | AC | GRC Team | Not Started | High
24 | Access Request Workflow | SLA for access request approvals defined — standard and emergency SLAs documented | AC | Business | Not Started | Medium
25 | Access Request Workflow | End-to-end access request workflow tested — full cycle from request to provisioning | AC | GRC Team | Not Started | High
26 | Access Request Workflow | Provisioning connection (CUP to PFCG/SU10) configured and validated | AC | Basis | Not Started | High
27 | Access Request Workflow | User communication sent — self-service access request training materials distributed | AC | GRC Team | Not Started | Medium
28 | Access Request Workflow | SoD check integrated into access request workflow — violations surfaced at request time | AC | GRC Team | Not Started | High
29 | Access Request Workflow | Role owner assignment complete — all roles have named business owners in GRC | AC | Business | Not Started | High
30 | Access Request Workflow | Access request workflow sign-off obtained from business and IT security | AC | GRC Team | Not Started | High
Emergency Access Management (Firefighter)
31 | Emergency Access Management (Firefighter) | Firefighter IDs (FFID) defined, approved, and provisioned — naming convention documented | EAM | Security | Not Started | High
32 | Emergency Access Management (Firefighter) | Firefighter controller assignments defined — each FFID has a named controller in GRC | EAM | Business | Not Started | High
33 | Emergency Access Management (Firefighter) | Firefighter log review process established — log reviewer assigned (separate from controller) | EAM | Business | Not Started | High
34 | Emergency Access Management (Firefighter) | Periodic firefighter log review schedule confirmed — minimum monthly review cadence | EAM | Business | Not Started | High
35 | Emergency Access Management (Firefighter) | Firefighter usage policy documented and distributed to all firefighter users and controllers | EAM | GRC Team | Not Started | High
36 | Emergency Access Management (Firefighter) | Firefighter log extraction and email delivery to reviewer configured and tested | EAM | GRC Team | Not Started | High
37 | Emergency Access Management (Firefighter) | Firefighter session logging validated — all transactions captured in CATT/STAD logs | EAM | Basis | Not Started | High
38 | Emergency Access Management (Firefighter) | Firefighter access request process defined — emergency access requires documented justification | EAM | Business | Not Started | High
39 | Emergency Access Management (Firefighter) | FFID assignment report scheduled — weekly distribution to IT Security and Audit | EAM | GRC Team | Not Started | Medium
40 | Emergency Access Management (Firefighter) | Firefighter policy exceptions (permanent FFIDs) documented and approved by CISO | EAM | Security | Not Started | Medium
Go-Live & Post-Go-Live
41 | Go-Live & Post-Go-Live | SOD report baseline run in PRD — full conflict report distributed to process owners | AC | GRC Team | Not Started | High
42 | Go-Live & Post-Go-Live | Conflict owners notified — each conflict has a named remediation owner with target date | AC | Business | Not Started | High
43 | Go-Live & Post-Go-Live | Remediation plan active — Critical conflicts remediated before go-live (or risk accepted) | AC | Business | Not Started | High
44 | Go-Live & Post-Go-Live | Periodic SOD review cadence set — quarterly minimum review by process and risk owners | AC | GRC Team | Not Started | High
45 | Go-Live & Post-Go-Live | Access certifications (UAR) process configured and first certification campaign launched | AC | Business | Not Started | High
46 | Go-Live & Post-Go-Live | Integration with HR system confirmed — new hire / termination feeds provisioning/deprovisioning | AC | Basis | Not Started | High
47 | Go-Live & Post-Go-Live | GRC Access Control connected to SAP authorization layer — provisioning validated end-to-end | AC | Basis | Not Started | High
48 | Go-Live & Post-Go-Live | GRC reporting distributed to stakeholders — management reports scheduled and delivered | AC | GRC Team | Not Started | Medium
49 | Go-Live & Post-Go-Live | Hypercare support plan active — GRC functional consultant available for 30 days post go-live | AC | GRC Team | Not Started | High
50 | Go-Live & Post-Go-Live | Post go-live review scheduled at Day 30 — open issues and optimization items catalogued | AC | GRC Team | Not Started | Medium
51 | Go-Live & Post-Go-Live | Internal Audit briefed on GRC implementation — demonstration of controls to audit team | AC | GRC Team | Not Started | High
52 | Go-Live & Post-Go-Live | GRC system documentation completed — configuration workbook, runbook, and admin guide | AC | GRC Team | Not Started | Medium
53 | Go-Live & Post-Go-Live | Knowledge transfer completed — internal GRC admin trained and capable of ongoing operations | AC | GRC Team | Not Started | High
54 | Go-Live & Post-Go-Live | SOD risk acceptance log maintained — all accepted risks documented with business sign-off | AC | Business | Not Started | High
55 | Go-Live & Post-Go-Live | Ongoing monitoring dashboard configured — key metrics (open conflicts, FFID usage, UAR completion) | AC | GRC Team | Not Started | Medium